## Risk Matrix
Risk management system
Risk Matrix |  | Severity |  |  |  |  | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood x Impact) | Mitigation Measures | Responsible Person
[7 empty] | Data Quality Issues: Inaccurate or incomplete data can lead to incorrect predictions. | Data | 4 | 5 | 20 | Implement rigorous data cleaning and preprocessing techniques. Use data augmentation to address imbalance issues. | Data Scientist
|  | Insignificant | Minor | Moderate | Major | Severe+K10:P21 | Bias in Data: Historical biases in the data could lead to unfair treatment of certain groups. | Data | 3 | 4 | 12 | Conduct thorough bias analysis and use techniques like re-weighting or re-sampling to mitigate bias. | Data Scientist
[7 empty] | Data Privacy and Security: Handling sensitive data requires strict adherence to privacy regulations. | Data | 2 | 5 | 10 | Anonymize personal data, implement strong encryption, and comply with GDPR. | Data Protection Officer
Likelihood | Almost Certain | Medium | High | Very High | Very High | Very High | Model Bias: The model may inherit biases present in the training data. | Model | 3 | 4 | 12 | Use fairness metrics to evaluate and mitigate biases. | ML Engineer
[7 empty] | Model Accuracy and Reliability: Inaccurate predictions can result in inappropriate responses to incidents. | Model | 4 | 5 | 20 | Use cross-validation, regular performance evaluation, and diverse datasets to ensure robustness. | ML Engineer
[7 empty] | Explainability: Lack of transparency in the model’s decision-making process. | Model | 3 | 3 | 9 | Use interpretable models where possible and employ techniques like SHAP or LIME to provide explanations. | ML Engineer
[7 empty] | Changes in Road Conditions: Variations in traffic patterns, weather conditions, or road infrastructure. | Operational | 4 | 4 | 16 | Implement redundancy and failover mechanisms. | Operations Manager
[7 empty] | System Downtime: Failures in the prediction system can lead to gaps in incident monitoring. | Operational | 3 | 5 | 15 | Ensure robust real-time data processing pipelines. | IT Manager
| Likely | Medium | High | High | Very High | Very High | Ethical Implications: Ethical concerns about AI in decision-making impacting public safety. | Ethical | 2 | 4 | 8 | Establish an ethics review board to oversee AI system deployment. | Ethics Officer
[7 empty] | Compliance with Regulations: Ensuring compliance with GDPR and the EU AI Act. | Legal | 2 | 5 | 10 | Stay informed about relevant regulations and ensure ongoing compliance. | Legal Advisor
[7 empty] | Performance Degradation: Model performance may degrade over time. | Monitoring | 4 | 4 | 16 | Regular model retraining using new data. | ML Engineer
[7 empty] | Anomaly Detection: Difficulty in detecting anomalies or edge cases. | Monitoring | 3 | 4 | 12 | Implement robust anomaly detection techniques and regular reviews. | Data Scientist
| Possible | Low | Medium | High | High | Very High
| Unlikelyh | Low | Low | Medium | Medium | High
| Rare | Low | Low | Low | Low | Medium

## Risk Matrix Key
Likelihood: Chance of risk
Rare: Slim possibility of happening
Unlikely: Could occur but remote
Possible: Might happen
Likely: Expected to occur
Almost Certain: Expected regularly
Severity: Impact on project
Insignificant: Not worth worry about
Minor: Can cause delays or added costs
Moderate: Likely delays or costs
Major: Possible failure
Severe: Definite failure
Risk Level: Setting Priority
Low: Not much risk
Medium: Some risk
High: Major risk
Very High: Extreme risk